## Аркуш1
Filled by Change requestor | Date: |  | Request for Change №
| Time: |  | Approved by:
| Status: |  | Category:
Requested by:
Description
Reasons for change
Effect if not implementing change
Services that will be affected
Filled by Change requestor | Date: | 2024-04-16 | Request for Change № | 1
| Time: | 7:00 - 7:30 am | Approved by: | Markiyan Prisyazhnik
| Status: | Approved | Category: | Minor
|  |  | Requested by: | DevOps
Description
Install Cisco routers patches
Reasons for change
Cisco manufacturer published new updates for our devices. This patch makes router work more stability.
Effect if not implementing change
Routers can sometimes lost connections for 20-30s
Services that will be affected
WIFI network in Financial and Marketing departments
Filled by Change requestor | Date: | 2024-04-20 | Request for Change № | 2
| Time: | 12:00 am - 4:00 pm | Approved by: | Markiyan Prisyazhnik
| Status: | Approved | Category: | Major
|  |  | Requested by: | IT manager
Description
Migrate data from old web server to new
Reasons for change
Old server starts working slowly. Sometimes server is unavailable.
Effect if not implementing change
Our web services will work slowly and will be unavailable for users when the server is overloaded.
Services that will be affected
Web app for ordering food
Filled by Change requestor | Date: | 2024-04-20 | Request for Change № | 3
| Time: | 1:00 pm - 2:00 pm | Approved by: | Markiyan Prisyazhnik
| Status: | Postponed | Category: | Medium
| Postponed: 6:00 - 8:00 pm |  | Requested by: | SOC engineer
Description
Installation Web application firewall on web server
Reasons for change
Our web server doesn't have protection from XSS attack and SQL Injection.
Effect if not implementing change
Treat actors can exploit this vulnerabilities and get access to database
Services that will be affected
Web app for ordering food